## Sheet1
Project Webfashion Cost Estimate
| #Units/Hrs | Cost/Unit/Hrs | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1. Project Management |  |  |  | 9328 | 7%
1.1 Project Manager | 48 | 16 | 768
1.2 Project Sponsor |  | 0 | 0
1.3 Business Analyst | 16 | 15 | 240
1.4 Web Designer 1 | 72 | 13 | 936
1.5 Web Designer 2 | 72 | 13 | 936
1.6 Database Programmer 1 | 72 | 13 | 936
1.7 Database Programmer 2 | 72 | 13 | 936
1.8 Senior Programmer | 16 | 20 | 320
1.9 Quality Specialist | 64 | 10 | 640
1.10 Senior Quality Specialist | 8 | 15 | 120
1.11 Testing Special 1 | 120 | 13 | 1560
1.12 Testing Special 2 | 112 | 13 | 1456
1.13 System Analysist | 32 | 15 | 480
2. Hardware
2.1 Computer | 5 | 1300 | 6500 | 6500 | 6%
3. Software
3.1 Licensed Software | 150 | 200 | 30000 | 34000 | 26%
3.2 Datebase | 2 | 2000 | 4000
4. Testing |  |  |  | 3400 | 3%
5. Training
5.1 Trainee Cost | 100 | 500 | 50000 | 50000 | 38%
6. Reserves |  |  |  | 26028 | 20%
Total Project Cost Estimate |  |  |  | 129256